## Sheet1
Task | Task Code | 2017 |  |  | 2018 | [11 empty] | 2019 | [8 empty] | Comments
|  | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
Komondor | KM | bar: 2017 10 to 2018 6
- v1.0 testing | KM1 | bar: 2017 10 to 2017 11
- v1.0 documentation (journal publication) | KM2 | bar: 2017 10 to 2017 11
- v2.0 (agents) | KM3 | bar: 2017 12 to 2018 2
- v2.1 (agents ++) | KM4 | bar: 2018 3 to 2018 6
SFCTMNG collaboration | CT | bar: 2017 10 to 2018 2
- Algorithm v1.1 | CT1 | bar: 2017 10 to 2017 11
- Algorithm v1.2 (optimal conf identification.) | CT1 | bar: 2017 12 to 2018 2
Decentralised Implications (Extension) | DL | bar: 2018 3 to 2018 5
- Apply CTMN to experiments | DL1 | bar: 2018 3 to 2018 4
- Write a letter extending previous results | DL2 | bar: 2018 5
Internship in UNAM | IN
- Landing, collection of requirements and review of the state-of-the-art | IN1
- Experimental setup, code development and analysis of the results | IN2
- Develop a journal publication with the state-of-the-art and the findings of task IN2 | IN2
NS3 | NS | bar: 2018 1 to 2018 10
- Learn basics | NS1 | bar: 2018 1 to 2018 2
- Translate results from Komondor | NS2 | bar: 2018 3 to 2018 10
Gather expertise on ML tools | ML | bar: 2017 10 to 2018 9
Project Plan Nacional | PN
FON Collaboration | FON
SoA | SOA | bar: 2018 5 to 2018 7
Refine SoA in TPC and CCA | SOA1 | bar: 2018 5
Publish paper SoA in TPC and CCA | SOA2 | bar: 2018 6 to 2018 7
Publication in TPC/CCA adjustment I | PB1 | bar: 2018 9 to 2019 1
Publication in TPC/CCA adjustment I | PB2 | bar: 2019 1 to 2019 6
DSA and TPC/CCA collaboration with Barrachina | CL1 | bar: 2019 1 to 2019 3
Write thesis | TH | bar: 2019 4 to 2019 9